## Tasks - Aven Zitzelberger
Roughly Estimated time range (work hours)
High-level task category | Task functinality or feature group | Task Details | Intended purpose of this task or the effect it will have | Priority of the task | Estimated difficulty. Higher difficulty means more uncertainty in the time estimates. | Minimum time for the most basic functionality. May be unstable, incomplete, or proof-of-concept. | Intermediate time for a stable version. | Upper estimate to fine-tune and polish, or if unexpected obstacles appear.
Category | Function | Task | Purpose | Priority | Difficulty | Basic | Stable | Polished
Infrastructure | Repository Rewrite | Write a developer CLI for running each part of the data pipeline seperately and all together. | This will streamline development of the data collection and processing, allowing me to more easily test and implement changes and new features. | 3 - High | Medium | 50 | 100 | 150
Infrastructure | Repository Rewrite | Remove hard-coded table schema in favor of a modular system defined outside of the pipeline internals. Write database and table classes for both Aurora and Redshift with identical method signatures for interchangeability. | This will streamline the collection of new types of data for the database, and the connections between databases. | 3 - High | Medium | 50 | 150 | 300
Infrastructure | Repository Rewrite | Integrate the RedShift warehouse into the pipeline, making it the destination for all data collection and extraction. Requires RedShift-specific table class which defines the table sorting and partition constraints unique to RedShift. | This will allow us to use the new RedShift database within BRAINWORKS. Currently the older, smaller Aurora database is still being used. | 3 - High | Hard | 50 | 100 | 200
Infrastructure | Repository Rewrite | There are many constraints placed on the transactional database which can no longer be enforced by RedShift, and must instead be enforced by the backend before insertion. Example: Duplicate PMIDs are being inserted into the documents table, which were previously removed automatically by virtue of the MySQL table schema. This resulted in some stuff like duplicate triple concepts from information extraction. Instances of redundancy like this need to be eliminated. | This will aid in making the transition to RedShift and improve efficiency of queries. | 2 - Medium | Easy | 40 | 80 | 160
Data | Repository Rewrite | Requires RedShift integration. Merge concept_map, definitions, and concept_embeddings tables (relating concept IDs to all relevant info for that concept). Current concepts table should then only relate triple IDs to concept IDs. Concepts table doesn't need the concept name, only the ID - remove redundant information. Rank order authorship in affiliations table. Using ROW_NUMBER() with a partition is really expensive and slows down queries with authorship. Need unique condition on the citations table over a combination of pmid and citedby, to ensure that we don’t get duplicate rows of one papers citing the same paper multiple times. | This will reduce the size of data stored and increase efficiency of queries involving paper concepts and authorship. | 2 - Medium | Easy | 10 | 20 | 40
Infrastructure | Repository Rewrite | Requires RedShift integration and CLI. Create pre-computed tables for each website tool to put on the transactional database, and CLI scripts to automcatically create them from the RedShift warehouse in the pipeline | This will allow a larger time range of data to be used for the website. | 2 - Medium | Medium | 10 | 40 | 80
Infrastructure | Repository Rewrite | Requires CLI. Write class for abstracted control of the parallel cluster (automating node number selection, instance type, deployment, etc..) | This will aid in more quickly configuring, testing, running, and automating the parallel computing cluster used for complex analysis on the collected data. | 2 - Medium | Medium | 20 | 40 | 80
Infrastructure | Database | Migrate RedShift database to same account that has access to the EC2 instance that hosts brainworks. | This will make dealing with the database connections less complicated. | 2 - Medium | Medium | 10 | 20 | 40
Infrastructure | Full Paper Text | Requires new RedShift schema and integration in pipeline. Data collection pipeline for obtaining full paper texts (without images or tables, as a first step). Additionally add new column to the triples table, matching that naming scheme to show which section of the paper it came from. | Adding full paper texts to the database. | 2 - Medium | Medium | 40 | 80 | 200
Algorithms | Full Paper Text | Incorporate all new paper sections in the information extraction pipeline. Optimizations will definitely be necessary to not slow everything down to unusable levels - may need to ramp up the parallel cluster resources significantly. | Implementing and optimizing the processing of full paper texts. | 2 - Medium | Hard | 80 | 200 | 400
Data | Website | Add a more feature-rich standard paper searching mechanism, similar to PubMed. The different for us being that any given paper could link to a citation network, triples, topic analysis, etc. | Adding the ability for users to search for papers the way they are used to, like on PubMed. This will be very important to the appeal and useability of the platform. | 2 - Medium | Medium | 100 | 200 | 400
Visual | Website | Improve errors for all tool search page (database error, result volume error, etc). | Improving instant user feedback to the search pages will be imporant to improving user experience. | 2 - Medium | Easy | 10 | 20 | 30
Algorithms | Novelty Metric | Next iteration of novelty metric. Create a LightGBM model for rough prediction based on select available features. | This is the next step in creating an algorithm that can predict novelty. This will tell us how viable it is to predict novelty based on basic statistics already in the database. | 2 - Medium | Medium | 40 | 80 | 160
Algorithms | Novelty Metric | Next iteration of novelty metric. incorporate information about the topic co-occurrences of each paper only up to the publication date. This will require concept embeddings or text vectorization to use as features for prediction. | This is the next step in creating an algorithm that can predict novelty. This will tell us whether novelty can be predicted using the concepts extracted from triples. | 2 - Medium | Hard | 40 | 200 | 400
Infrastructure | GraphAPI | Update GraphAPI to version 0.0.3 with updated callback functions for interaction events, including toolbar buttons. Also add empty callbacks for complete customization. | This version of the graph visual will aid developers in creating a more customizable experince integrated with the website. | 2 - Medium | Easy | 10 | 20 | 40
Infrastructure | GraphAPI | Solve issues with GraphAPI not working on mobile | Will need to implment touch interaction and modifications to the display layout for small screens. | 2 - Medium | Hard | 40 | 80 | 160
Data | Tools | Triple graph needs an additional recursive level of searching (or more). | Would allow users to add nodes and edges to the triple graph by clicking a "see more" button, similar to the topic co-occurrence grpah. | 2 - Medium | Easy | 10 | 20 | 30
Data | Tools | Improvements to the Topic Co-occurrence graph: Extra nodes added afterward must be constrained by the exlude_topics parameter. Adjust delta threshold for including connections in the initial plot to make the concepts first displayed more relevant. Maybe add this as an interactive element (would require new features for the GraphAPI)? Increase time range of pre-computed table once data is available. | Bug fixes and improvements for the topic co-occurrence graph | 2 - Medium | Easy | 10 | 40 | 80
Infrastructure | Website | Implement a user dashboard. Requires database table for storing the complete graph structure for the N most recent searches of each user. Will also need a column for storing a low-res thumnail of the plot for display and other information necessary for the dashboard page | New feature idea: Personal Dashboard. Users will be able to see their recent searches, view past graphs generated, and save graphs permanently. | 1 - Low | Hard | 100 | 200 | 400
Visual | Website | Add accessibility features to the website like font control, text-to-audio, color-blindness configuration option, and keyboard navigation. | Improving the accessibility of the website will be important to reduce the bias of individuals who are able to use it and improve user experience. | 1 - Low | Medium | 100 | 200 | 400
Visual | Website | Move collection of user information to an on-boarding process that occurs after signup and email verification. | Reducing the steps necessary for user signup will increase acquisition and the liklihood that users follow-through the process. | 1 - Low | Easy | 20 | 100 | 200
Infrastructure | Database | Try out GraphQL as a method for storing recursively-connected data, like citations and triples. | Moving a subset of the data to another type of database more suited for it has the potential to greatly increase the amount of data that can be available for the website. | 1 - Low | Hard | 100 | 200 | 800
Infrastructure | GraphAPI | Separate physics sim from cluster tree - sim shouldn't be dependent on the tree being constructed on graph initialization. | Optimizations for the graph visual. | 1 - Low | Easy | 10 | 20 | 40
Infrastructure | GraphAPI | GraphAPI version 0.0.4: Add documentation with collapsible elemenets for developers. Make clear that cluster arguments are the key values. Walk through building process of the repository. Give examples of JSON and subsequent image. Remove upload feature - cannot serialize callback functions for transfer (this functionality will essentially be replaced by the BW website saved graphs feature). Should cluster aggregate options apply to the data properties instead of the resulting visual attribute (size and color)? Also need the option to determine how property filters function across the board for clusted nodes/edges (min, max, average, etc.) | The next version of the graph visual will help improve developer access and user experience. | 1 - Low | Easy | 40 | 80 | 200
Infrastructure | Website | User searches table must store the full search query in JSON format (currently has seperate columns for various parts of the query, which is not sustainable for adding new tools) | Future-proofing the user searches database for the addition of new tools. | 1 - Low | Easy | 10 | 20 | 30
Data | Tools | Need to rewrite citation query. For some reason, sometimes the author info is getting lost when doing the citation query. This is noticeable when the paper_info page has the author information, but the citation network graph does not. Potentially a bug in the author filtering mechanism. | Bug-fixing and optimization of the citation network query. | 1 - Low | Easy | 10 | 20 | 40
Data | Tools | Requires RedShift integraion and CLI. Need pre-computed autocomplete tables for authors, grants, journals, etc. | Adding autocomplete when searching for authors, grants, journal titles, etc. | 1 - Low | Medium | 20 | 40 | 80
Algorithms | Repository Rewrite | Experiment with the using the constituency parse tree rather than OpenIE dependency parsing. I think I've come up with a way to more proceedurally generate triples from the parse tree that are more predictable and would allow much further fine-tuning. | Potential direction for improving the triple extraction from text. | 1 - Low | Hard | 50 | 200 | 400
Data | Repository Rewrite | Add MeSH and UMLS heirarcical structure to the database. Can be used to provide information on the topic co-occurrence graph about what percentage of a particular topic consists of publications of a particular type, geographical region, etc. | Adding heirarchical information to the UMLS and MeSH topics will allow more information about paper topic clusters to be displayed on the website. | 1 - Low | Hard | 50 | 100 | 200
Data | Data Collection | Improve publication date when parsing PubMed data (again). The previous improvements helped, but I think I can get better resolution by cross-referencing with citation datesa and journal publication dates. Could be an interesting project. | There is potential for improving the resolution of publication dates beyond those available on PubMed. | 1 - Low | Hard | 100 | 200 | 400
Infrastructure | Repository Rewrite | Verify a suitable overlap between the publications/documents table and the citations table. When last checked, there were some inconsistencies that need to be addressed, like that some PMIDs in the citation table did not exist in the documents table. This could be a result of left-over entries from previous runs of the pipeline, or maybe loss of information during document collection. Either way, the CLI should help with testing and fixing this. | Fixing some bugs and unexplained behavior in the document collection process. | 1 - Low | Medium | 20 | 40 | 80
Infrastructure | Website | Switch to Redis for an in-memory session database. The hard part is setting up Redis on the production/staging environment. Does there need to be an install script that runs on deployment or can we install it once and forget about it? I predict there will also be port shennanigan to deal with within the VPC. | This will improve speed and reliability of user information being retrieved on the website. | 1 - Low | Hard | 20 | 40 | 80
Other | Website | Either use a third-party captcha system or further improve our own. | The captcha helps prevent automated hacking systems from brute-forcing our authentication measures. Improving this is good practice for the long-term health of the platform. | 1 - Low | Medium | 20 | 40 | 80
Infrastructure | GraphAPI | Remember each user's settings from last time locally (client-side storage) | Improving the user experience by using the GraphAPI itself to store interface options within the graph visual. | 1 - Low | Easy | 10 | 20 | 40
Infrastructure | GraphAPI | Find a better way to communicate events past the iframe barrier when requesting the main graph object. The current method is real bad for a few reasons. First, if the host doesn't define the graph in the global scope, I can't see it (in the window object) in order to swap it out with the actual graph object. Second, if the host passes the graph instance to a function before it's ready, it won't be replaced by the inner gaph instance. Currently you need to use the graph.ready() function to configure everything because you need to wait for it to make the secret secondary request for the actual JS data. This is necessary because we need to load the actual JS into the scope of the iframe, which the host doesn’t have access to because it’s created by the loader. Another possibility might be to do it the other way around - have the loader grab the real graph object from the inner scope and replace itself? This is still real messy and needs a more elegant solution. | Some major rewrites of the graph visual tool are necessary for long-term viability and robustness. | 1 - Low | Hard | 50 | 100 | 200
Infrastructure | GraphAPI | Need to rewrite the dimension mapping module. Write mapper class with all method necessary to perform a mapping for any node/edge data property. Each method should take in an object with key value pairs for arguments so it can be easily converted to and from JSON format. Should have one function that takes in a node/edge attribute object and returns that object but mapped according to all the currently active mappings. This could then be used to make the mappings rendered in a reducer! Also, when I implement a user-interactive mapping mechanism, the interface would only then have to talk to the mapper class to make changes, and because those visual changes are in a reducer, they would be reflected live. I experimented with a different generalized map_dimension() method that just takes in a callback function that itself converts a data value to a property value. Then the specific mapping function (color, size, whatever) can define whatever callback it wants according to its needs. JSON mapping should stay syntactically the same. Instead of having the validate_map_arguments() method, just call the requested function directly and pass the arguments object into it so each function can perform argument validation on its own. Will probs need to write a validation function that can be called in both the edge/node version of a mapper, like this.validate_color_arguments() and whatnot. | Some major rewrites of the graph visual tool are necessary for long-term viability and robustness. | 1 - Low | Hard | 100 | 200 | 400
Visual | GraphAPI | When selecting shortest path between multiple nodes, instead of showing a data display with a tab for each, show the data display for a single node and use the arrow keys to move back and forth. Improvements to the UI will be necessary as well as some new callback functions for the user input. | Improving the user experience for the graph visual. | 1 - Low | Easy | 10 | 20 | 30
Infrastructure | GraphAPI | Add usage tracking statistics to GraphAPI | Having the ability to track use of the graph tool itself will provide useful insights into potential improvements to the user experience. | 1 - Low | Medium | 20 | 40 | 80
Infrastructure | GraphAPI | Handle selection of branch nodes before and after expanding it. Currently there is no mechanism for seleting multiple nodes, but maybe that should be the case. | Improving the user experience for the graph visual. | 1 - Low | Hard | 10 | 20 | 40
Infrastructure | GraphAPI | Find a good unit testing library. Should be able to: Test the functionality of each individual component (dimension_mapper, interaction, etc). Generate, take, and compare screenshots of a virtual browser window. Simulate user interactions like clicks and mouse movements. I’ll need to make sure that my modules are adequately separated because I can’t test just the javascript if there is jQuery stuff attached and whatnot. | Automated testing of the graph visual will be necessary as more features are added and testing takes longer. | 1 - Low | Hard | 50 | 100 | 200
Visual | GraphAPI | Need a method to show edges between sub-nodes and branches at different levels. | The clustering mechanism used by the graph cannot visualize connections across cluster levels. Implementing this will allow for much better interpretation of any given graph which uses clustering. | 1 - Low | Hard | 50 | 100 | 400
Visual | GraphAPI | I added the ability to traverse the tree one level at a time, but I really want to be able to go to any tree level from any other tree level. Then I could put the vertical slider back and allow double clicking to change the tree depth (in open_node()). When a single node is opened, move to that tree depth and zoom in (should be disablable in user settings). More nodes that would open to that depth do not zoom. Moving back up closes nodes at that depth. Double clicking should be like using the buttons except it’s just one node, and you can use the buttons to get back out. For now, I just made the buttons increment/decrement the tree depth (bounded from 0 to height). The problem is that this means if a lower level node is opened by double-click, using the expand button might actually close it. Could write two different set_depth() functions, for expanding and collapsing. This would allow me to keep lower level nodes open when expanding, but not when collapsing. | The mechism for opening and closeing the clustering of a graph is not very fluid, and some restructuring is required to make this more flexible. | 1 - Low | Hard | 20 | 40 | 80
Visual | GraphAPI | When moving the whole tree down a level, animate all expansions together instead of one at a time? Might be less laggy. | Improving the methods used to animate clusters expanding and contracting will improve performance. | 1 - Low | Medium | 10 | 20 | 40
Visual | GraphAPI | Implement dynamic node/edge properties which can change with a slider. The idea is that data properties would be allowed to be arrays of values instead of a single value. Then a new type of slider is associated with that list, and iterates through the different values, effectively changing the value of each node/edge. This is different than the current method because them a mapper which updates in the reducer would react live, changing mapped node/edge properties accordingly. This would give the graph another dimension to work with when representing data. | This would add the ability for a time-component to any graph visual. A user could move a slider and watch the graph properties change over time. Major restructuring would be required to implment this. | 1 - Low | Hard | 100 | 200 | 400
Infrastructure | GraphAPI | Add module for node/edge shape as a customizable dimension for mapping. This will require writing the renderer from scratch as there is no native way to do this in sigma. | Adds the ability to change the node shape in graph visuals. This could help differentiate categorical variables in a dataset. | 1 - Low | Hard | 20 | 100 | 200
Algorithms | Database | Full ML sentiment analysis for triple relations | Implementing machine-learning algorithms to analyse the sentiment of triple relations could prove very useful in thinning and organizating the triple graph and make it easier to interpret. | 1 - Low | Medium | 100 | 200 | 400
Algorithms | Projects | Need a method of uniquely identifying all authors with same name using our own identification system. This should use information about a given author's publication history, locations, timeline, co-authors, citation network, etc. Potential for ML applications? This is itself a big project. | Ideas for uniquely identifying all authors within our system. This is an ongoing area of research and is potentially a massive undertaking, but would provide an incredibly useful service. | 1 - Low | Hard | 200 | 500 | 1000
Data | Projects | Parse and catalogue data repositories and links from papers, and track citations of that dataset in other publications. This will require pulling data from many known public resources that track various standards of dataset citing. Additionally, it would be ideal to write an algorithm to detect links/citations to data repositories within the text of a paper. Major project. | Having the ability to detect, track, and display citations to data respositories within publications using a single unified system is currently an open and relatively unexplored area of development. This could be a major feature that BRAINWORKS provides. | 1 - Low | Hard | 200 | 500 | 1000